## How to use
Weekly PMO reporting template
Template offered by THG Conseil · Tudor Hilcu, founder and head of THG Conseil · thgconseil.fr
What it is for
A summary page for the steering committee, fed by four registers: milestones, risks, decisions and budget. The project manager keeps the registers; the summary calculates itself, except for the RAG status and comments, which remain a judgement.
The weekly routine
1 | Summary: enter the report date. Overdue milestones and decisions are calculated from it.
2 | Milestones: update forecast dates, actual dates and statuses; add new milestones.
3 | Risks: review the probability, impact, response and status of each open risk; add new ones.
4 | Decisions: record each pending decision with its decision maker and deadline; update those that have been made.
5 | Budget: enter planned to date, actual to date and estimate to complete for each item.
6 | Summary: set the status of each area, then the overall status, and write a few lines on highlights, points of attention and next steps.
Reading the status
· | Green: the project is holding its plan.
· | Amber: there is a gap, actions are under way, no decision needed.
· | Red: the plan no longer holds without a decision or arbitration by the committee.
Cells
Input cell: drop-down lists for status, statuses and scores.
Calculated cell: protected, it updates by itself.
Red | Alert: overdue milestone or decision, critical risk, budget overrun, “Red” status.
Tips
· | Risk score = probability (1 to 4) × impact (1 to 4). Level thresholds can be changed at the top of the “Risks” tab.
· | A pending decision always has a named decision maker and a deadline; without a date, it does not show in the summary.
· | The “Fictitious example” lines at the top of each register show the expected format; they are not counted.
· | To add rows or columns, unprotect the sheet (Review menu, Unprotect Sheet: there is no password), then check the ranges of the summary formulas.
A part-time PMO
Part-time PMO, one to two days a week: governance and committees, master schedule, risk register, weekly dashboard. Call me or write to me. The first conversation is complimentary, within 48 hours.
thgconseil.fr/en/contact · +33 6 74 86 88 70 · contact@thgconseil.fr
Tudor Hilcu, founder and head of THG Conseil. Eight years running programmes, portfolios and budgets for major groups. PMP®, PRINCE2 Agile®, ITIL® 4. Template version 1.0, October 2026.

## Summary
Weekly PMO report
One page for the steering committee: where the project stands, what threatens it, what needs deciding. Only the RAG status and comments are entered here; the rest comes from the other tabs.
Project or programme |  |  |  | Report date
Sponsor |  |  |  | Week or period
Project manager or PMO |  |  |  | Next committee
RAG status
Area | Status | Trend | Comment
Overall status
Schedule
Budget
Scope and quality
Risks
Team and resources
Green: the project is holding its plan. Amber: there is a gap, actions are under way. Red: the plan no longer holds without a decision or arbitration by the committee.
Progress and milestones
Planned progress to date |  |  |  | Milestones achieved
Actual progress to date |  |  |  | Milestones overdue
Gap (actual minus planned) |  |  |  | Open dated milestones
Next milestones | Date | Owner |  | Status | Alert
Risks
Open risks |  |  |  | Open risks matrix (count)
of which critical |  |  |  |  | 1 | 2 | 3 | 4
of which high |  |  |  | 4
3
2
1
Most critical risks | Score | Level | Owner | Response
Pending decisions
Decisions to make |  |  |  | of which overdue
Pending decision | Deadline | Decision maker |  | Alert
Budget
Baseline budget |  |  |  | Estimate at completion
Planned to date |  |  |  | Variance at completion (estimate minus budget)
Actual to date |  |  |  | Share of budget spent
Variance to date (actual minus planned) |  |  |  | Unit
Highlights and next steps
Highlights of the week
Points of attention and arbitration needed
Next steps

## Milestones
Milestones
A milestone is a verifiable result on a date. Delays are calculated from the report date (“Summary” tab).
Report date
No. | Milestone | Owner | Baseline date | Forecast date (revised) | Actual date | Status | Variance (days) | Alert | Comment
Ex. | Fictitious example: user acceptance signed off | Business owner |  |  |  | In progress |  |  | Fictitious example: line not counted, for format only.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Risks
Risk register
Score = probability × impact, from 1 to 16. A closed risk stays in the register for the record.
Probability: 1 unlikely · 2 possible · 3 likely · 4 almost certain
Impact: 1 minor · 2 moderate · 3 significant · 4 major
| Level thresholds (editable): | Critical ≥ | 12 | High ≥ | 8 | Medium ≥ | 4
No. | Risk (cause, event, consequence) | Category | Owner | Probability (1 to 4) | Impact (1 to 4) | Score | Level | Response and actions | Due date | Status | Last review
Ex. | Fictitious example: the supplier delivers the interface late, testing slips. | Suppliers | Project manager | 3 | 3 | 9 | High | Fictitious example: weekly supplier check-in, costed plan B. |  | Open
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Decisions
Pending decisions
A pending decision has a named decision maker and a deadline. A decision made stays in the register, with its date.
Report date
No. | Pending decision | Options and recommendation | Requested by | Decision maker | Deadline | Status | Decision made | Decision date | Impact if delayed | Alert
Ex. | Fictitious example: approve moving release 2 by one month | Option A: move; option B: reduced scope. Recommendation: A. | PMO | Sponsor |  | Pending |  |  | Fictitious example: testing delayed.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Budget
Budget
Baseline budget = revised budget if approved, otherwise initial budget. Estimate at completion = actual + estimate to complete.
Unit of amounts | EUR excl. VAT
Item | Initial budget | Revised budget (approved) | Baseline budget | Planned to date | Actual to date | Variance to date | Estimate to complete | Estimate at completion | Variance at completion | Share spent | Comment
Fictitious example: external services (line not counted)
Internal team (costed days)
External services
Licences and subscriptions
Hardware and infrastructure
Training and change management
Travel and sundry
Contingency
Total