## How to use
The project on one page
Free module · Tudor Hilcu, by THG Conseil · thgconseil.fr
What to fill in, and in what order
1 | “Project sheet”: at launch, fill in the five boxes, then have the sheet reviewed by the one who pays and the one who delivers. Allow an hour.
2 | “Decision log”: for each decision, one line with the date, who decides, why and the deadline. Five minutes per decision.
3 | “Portfolio status”: every week, one line per project (progress, budget, major risks, next deadline). The status calculates itself.
4 | “Go or no-go”: 48 hours before a cutover, answer the five questions. Five yeses, you go; otherwise you postpone and tell your customers.
5 | “Fictitious example”: a made-up project, filled in from start to finish, to see the result before you start.
Cells
Input cell: your text, dates, amounts; drop-down lists for answers and statuses.
Calculated cell: protected, it updates by itself.
Red | Alert: incomplete box, “postpone” verdict, “Red” status, overdue decision.
Good to know
· | The status thresholds can be changed at the top of the “Portfolio status” tab.
· | To add rows, unprotect the sheet (Review menu, Unprotect Sheet: there is no password), then check the formulas.
· | The step-by-step guide (PDF) explains each tab with screenshots, and walks through the fictitious example figure by figure.
An outside view
To frame a project, prepare a go or no-go or keep a portfolio status: call me or write to me. The first conversation is complimentary, within 48 hours.
thgconseil.fr/en/contact · +33 6 74 86 88 70 · contact@thgconseil.fr
Tudor Hilcu, founder and head of THG Conseil. PMP®, PRINCE2 Agile®, ITIL® 4. Module version 1.0, October 2026.

## Project sheet
Project sheet
Five boxes to fill in before launch. If the project does not fit on this page, it is not ready to start.
| Project | [5 empty] | Sheet drawn up on
1 | The objective, in one sentence, with a number |  |  |  | What will have changed, by how much, and by when.
Check
2 | The budget, with a line for contingencies |  |  |  | Contingency is a separate line, not a margin hidden in every item.
| Budget, excluding contingency |  | Contingency | Total |  |  |  | Check
3 | The date, and what happens if it slips |  |  |  | Write down what a month’s delay costs: money, customers, a missed season.
| Planned end date |  | Time left |  |  |  |  | Check
If it slips by a month
4 | The owner: one person only |  |  |  | A name, not a department or a committee.
| Name |  |  |  | Role |  |  | Check
5 | The three main risks, and the response to each |  |  |  | The risk: what could happen. The response: what you do before it happens.
No. | Risk |  |  |  | Response |  |  |  | Check
1
2
3
| Review, before launch |  |  |  | If they disagree on a box, talk about it now, not after launch.
| Reviewed by | Name |  |  | Date | Agreed? | Disagreement or reservation
The one who pays
The one who delivers
| Boxes filled in |  | Where the sheet stands

## Decision log
Decision log
One line per decision: what was decided, by whom, why and by when. In six months, nobody will remember the why.
| Review date |  | Used |  |  | Leave blank: today’s date is used.
| Open decisions |  | Overdue |  | Review due
No. | Decision | Who decides | Date | Why |  |  | Deadline | Status | Review on | Alert | Follow-up
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Portfolio status
Portfolio status
One line per project, updated every week. The status is calculated from four criteria and thresholds you can change.
| Review date |  | Used |  |  | Leave blank: today’s date is used.
| Criterion | Amber from | Red from | How to read it
| Progress behind plan (points) | 5 | 15 | Actual progress minus planned progress. Actual 50%, planned 60%: 10 points behind.
| Budget overrun | 5% | 15% | Budget spent compared with the budget planned for the same date.
| Open major risks | 2 | 4 | Risks that threaten the date or the budget and whose response is not in place.
| Deadline overdue (days) | 1 | 15 | Days since the next deadline, when it has passed without being met.
A project’s status is that of its worst criterion. Green: everything within thresholds. Amber: a gap, to watch closely. Red: a decision is needed.
| Portfolio | Green |  | Amber |  | Red |  | To fill in
No. | Project | Owner | Planned progress | Actual progress | Gap (points) | Budget planned to date | Budget spent | Budget gap | Open major risks | Next deadline | Status | Why
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Go or no-go
Go or no-go, 48 hours before cutover
Five questions. Five yeses, you go. A single no or a single unclear answer, you postpone and tell your customers.
| Project |  |  |  |  | Decision made by
| Cutover date (D-day) |  | Decide by (48 hours before)
Decision made on
No. | Question |  |  |  | Answer | Evidence, or what is missing | Who confirms it
1 | Has the last full test run, from order to invoice, passed?
2 | Are the key people trained, and available on the day?
3 | Do your biggest customers have stock in hand?
4 | Is the rollback ready, and until when does it remain available?
5 | Who can say stop?
Rollback available until (date and time)
The person who can say stop
| Yes | No |  | Unclear | No answer
Verdict
| New cutover date |  | Customers told on

## Fictitious example
Fictitious example: the project on one page
Fictitious example: the company, project, names, amounts and dates are made up to show how the workbook works. Your own projects go in the other tabs.
Example company (fictitious): industrial supplies wholesaler, 45 staff, three branches. Project: replace the sales management software (quotes, orders, stock, invoices).
A · Project sheet
| Project | New sales management software (fictitious example) | [5 empty] | Sheet drawn up on |  | 2026-10-05
1 | The objective, in one sentence, with a number |  |  |  |  | What will have changed, by how much, and by when.
| Record every order and every invoice in the new software by 1 February 2027, and cut the time between delivery and invoice from 4 days to 1 day. | [8 empty] | Check
2 | The budget, with a line for contingencies |  |  |  |  | Contingency is a separate line, not a margin hidden in every item.
| Budget, excluding contingency | 180000 | Contingency | 27000 | Total |  |  |  |  | Check
3 | The date, and what happens if it slips |  |  |  |  | Write down what a month’s delay costs: money, customers, a missed season.
| Planned end date | 2027-02-01 | Time left | [6 empty] | Check
| If it slips by a month | Old software licence extended by three months: €4,500. After 15 March the busy season starts: no cutover before September.
4 | The owner: one person only |  |  |  |  | A name, not a department or a committee.
| Name | Claire |  |  |  | Role | Finance and administration director |  |  | Check
5 | The three main risks, and the response to each |  |  |  |  | The risk: what could happen. The response: what you do before it happens.
No. | Risk |  |  |  |  | Response | [5 empty] | Check
1 | Item and customer data migration is incomplete: orders blocked on D-day. |  |  |  |  | Two trial migrations, in November and January; check of the 200 best-selling items.
2 | Sales staff are not trained in time: quotes redone by hand in February. |  |  |  |  | Training in December; two super-users per branch.
3 | The link with the carrier does not work: deliveries not triggered. |  |  |  |  | End-to-end test in January; delivery notes sent by email as a fallback.
| Review, before launch |  |  |  |  | If they disagree on a box, talk about it now, not after launch.
| Reviewed by | Name |  |  |  | Date | Agreed? | Disagreement or reservation
| The one who pays | Marc, managing director |  |  |  | 2026-10-07 | Yes
| The one who delivers | Julien, integrator’s project manager |  |  |  | 2026-10-08 | Yes | Data must be supplied before 30 Nov 2026.
| Boxes filled in |  | Where the sheet stands
B · Decision log
| Review date | 2027-01-29 | Used |  |  | Leave blank: today’s date is used.
| Open decisions |  | Overdue |  | Review due
No. | Decision | Who decides | Date | Why |  |  |  | Deadline | Status | Review on | Alert | Follow-up
1 | Choose integrator B for the new software | Management committee | 2026-10-12 | Offer €12,000 cheaper and three references in wholesale. |  |  |  | 2026-10-31 | Applied |  |  | Contract signed on 28 Oct 2026.
2 | Keep the old software read-only for twelve months after cutover | Marc, managing director | 2026-11-09 | Find past orders and invoices. Accountant asked for advice on record keeping. |  |  |  | 2027-02-15 | In progress | 2027-01-26
3 | Train two super-users per branch | Claire | 2026-12-07 | Sales staff hardly available in January. |  |  |  | 2027-01-15 | Applied |  |  | Six super-users trained.
4 | Bring in a contractor for the data migration | Claire | 2027-01-11 | Item migration three weeks behind. |  |  |  | 2027-01-25 | In progress
5 | Move cutover from 1 to 15 February and tell the five biggest customers | Marc, managing director | 2027-01-28 | Go or no-go of 28 Jan: question 3 unclear, stock in hand not confirmed by two customers. |  |  |  | 2027-02-15 | In progress | 2027-02-08 |  | Customers told on 28 Jan 2027.
C · Portfolio status
| Review date | 2027-01-29 | Used |  |  | Leave blank: today’s date is used.
| Criterion | Amber from | Red from | How to read it
| Progress behind plan (points) | 5 | 15 | Actual progress minus planned progress. Actual 50%, planned 60%: 10 points behind.
| Budget overrun | 5% | 15% | Budget spent compared with the budget planned for the same date.
| Open major risks | 2 | 4 | Risks that threaten the date or the budget and whose response is not in place.
| Deadline overdue (days) | 1 | 15 | Days since the next deadline, when it has passed without being met.
A project’s status is that of its worst criterion. Green: everything within thresholds. Amber: a gap, to watch closely. Red: a decision is needed.
| Portfolio | Green |  | Amber |  | Red |  | To fill in
No. | Project | Owner | Planned progress | Actual progress | Gap (points) | Budget planned to date | Budget spent | Budget gap | Open major risks | Next deadline | Status | Why
1 | New sales management software | Claire | 90% | 85% |  | 170000 | 176000 |  | 1 | 2027-02-15
2 | Warehouse move | Karim | 40% | 22% |  | 60000 | 58500 |  | 3 | 2027-01-15
3 | Online shop for tradespeople | Sophie | 30% | 32% |  | 25000 | 30000 |  | 0 | 2027-03-31
4 | Team leader training | Paul | 60% | 60% |  | 8000 | 7600 |  | 0 | 2027-03-12
5 | New transport contract | Nadia | 75% | 72% |  |  |  |  | 2 | 2027-02-05
D · Go or no-go
| Project | New sales management software (fictitious example) | [5 empty] | Decision made by |  | Marc, managing director
| Cutover date (D-day) | 2027-02-01 |  | Decide by (48 hours before)
| Decision made on | 2027-01-28
No. | Question | [5 empty] | Answer | Evidence, or what is missing |  |  |  | Who confirms it
1 | Has the last full test run, from order to invoice, passed? | [5 empty] | Yes | Full test run on 22 Jan: 40 orders, from entry to invoice. |  |  |  | Claire
2 | Are the key people trained, and available on the day? | [5 empty] | Yes | 12 people trained; schedule for the week approved. |  |  |  | Branch managers
3 | Do your biggest customers have stock in hand? | [5 empty] | Unclear | Two of the five biggest customers have not confirmed their stock in hand. |  |  |  | Sales team
4 | Is the rollback ready, and until when does it remain available? | [5 empty] | Yes | Old software kept open for entry until 2 February, 12:00. |  |  |  | Integrator
5 | Who can say stop? | [5 empty] | Yes | Marc, on Claire’s advice. |  |  |  | Marc
| Rollback available until (date and time) | [5 empty] | 2027-02-02 12:00
| The person who can say stop | [5 empty] | Marc, managing director
| Yes |  | No |  | Unclear |  | No answer
Verdict
| New cutover date | 2027-02-15 |  | Customers told on |  |  |  | 2027-01-28
Formulas:
Why = IF([Name]="",TODAY(),[Name])